Youth Skills and Employment Programme (fictional sample) — Logical Framework, 2025–2028

Implementing organisation: Sample Skills Foundation (fictional)

| Level | Code | Result statement | Indicator | Unit | Baseline | Baseline year | Target | Target year | Means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal | G | Young people in the two target regions secure decent and sustainable livelihoods | Youth unemployment rate in target regions | % | 31 | 2024 | 22 | 2028 | National labour force survey | Macroeconomic conditions remain stable |
| Outcome | 1 | Graduates of the programme are in employment or self-employment | Graduates employed or self-employed six months after completion | % |  |  | 65 | 2028 | Tracer study | Employers continue to recruit |
| Outcome | 1 |  | Average monthly income of employed graduates | USD | 120 | 2024 | 190 | 2028 | Tracer study |  |
| Output | 1.1 | Market-relevant technical and vocational training delivered | Young people completing accredited training | people | 0 | 2024 | 6000 | 2028 | Training records |  |
| Output | 1.1 |  | Share of trainees who are young women | % |  |  | 50 | 2028 | Training records |  |
| Output | 1.2 | Work placements and apprenticeships arranged with employers | Apprenticeships completed | apprenticeships | 0 | 2024 | 1800 | 2028 | Employer agreements; placement logs | Employers provide placements |
| Outcome | 2 | Youth-led micro-enterprises grow and survive | Youth enterprises still trading after two years | % | 40 | 2024 | 60 | 2028 | Enterprise survey |  |
| Output | 2.1 | Start-up grants and business mentoring provided | Enterprises receiving a start-up grant | enterprises | 0 | 2024 | 900 | 2028 | Grant register |  |
| Output | 2.1 |  | Mentoring sessions held | sessions | 0 | 2024 |  |  | Mentor logs | Volunteer mentors remain available |
| Activity | 1.1 |  | Develop curricula with industry; accredit training centres; enrol and train cohorts |  |  |  |  |  |  |  |
| Activity | 2.1 |  | Run business-plan competitions; disburse grants; match mentors |  |  |  |  |  |  |  |